## 1-Community Engagement
Strategy 1A. Increase outreach to new and existing Businesses and Corporations in NWSRA footprint
Goal | Department | Point Person | Quarter Objective | Objective Completed
Build relationships with businesses and corporations within Hoffman Estates community and surrounding area to support new NWSRA programming space. | SLSF | Liz | Q1: Attend 2 HE chamber events Q2: Volunteer at 2 HE events Q3: Attend 2 HE Chamber events Q4: Attend 2 HE chamber events | Q1: Luncheon (1/13), Awards (1/20), Wednesday event(1/26), Mayor's Update (2/22), Wednesday event (2/16), Multi Chamber (3/1) Q2: Village Networking (4/13), Bon Apetit (4/21), Multi Chamber (4/21), After Hours (4/28), Multi Chamber (5/3), Village Networking (5/10), Multi Chamber (5/18), Chamber Event (6/9), Rotary Club of Schaum-HE (6/10) Q3: Village Networking (7/27), SBA Savour Event (8/25), Multi-Chamber (8/22)
Strategy 1B. Increase outreach to new and existing individual donors in NWSRA footprint
Goal | Department | Point Person | Quarter Objective | Objective Completed
Continue development of Event 10 program. Develop the "Did You Know" campaign to increase communication among individuals identified within the Event 10 program and Database 10 program | SLSF | Liz/Megan | Q1: Develop marketing materials for "Did You Know" Campaign. Q2: Contact all event 10 from 2021 Q3: Start to create 2022 event 10 Q4: Finalize 2022 event 10 | Q1: Completed Did You Know flyer and sent to all civic groups Q2: Sent all Event 10 donors Did you Know flyer when asking for new contributions Q3: Event 10 donors have been identified from Fall events and will be contacted.
Superintendent of Development to examine database of existing donors | SLSF | Anne | Q1: Review donors from 2016-2021 Q2: Review donors from 2010-2015 Q3: Organize into categories Q4: Add to database for reporting | Q1: Donor Categories chosen: will segment donors into giving preference based on 5 pillars. Reviewing donors 2016-2021. Q2: Reviewing donors from 2010-2015 Q3: Continuing to review donors from 2010-2021, may delay to coincide with new crm in 2023.
Target PURSUIT, Inclusion families, STAR Academy families, Snoezelen Sensory Room, Day Camp families | SLSF/NWSRA Management Team | Liz | Q1: Choose groups to target for 2022 misc. fundraisers Q2: Work with day camp for pasta Q3: Target inclusion and programs for end of year quotes Q4: Work with PURSUIT for popcorn | Q1: Sent memo to TC about new ideas. Added sockathon (inclusion) and steps for success (PURSUIT) Q2: Met with Superintendent of Recreation to coordinate Fun Pasta Fundraiser, held 7/10-7/31 Q3: Target all programs for quites and stories push
Strategy 1C. Strengthen relationship with Booster Club to engage new families
Goal | Department | Point Person | Quarter Objective | Objective Completed
Redevelop Booster Club to align their goals with the overall direction of SLSF fundraising efforts | SLSF/ Superintendent of Recreation | Liz/Rachel | Q1: Communicate new plan to all Q2: Start contact with all Athletes families Q3: Develop relationships with families Q4: Request feedback for 2023 | Q1: Held meeting with Laurel (2/2). First newsletter went out. Q2: Started contact with all Athlete families. Q3: Coordinated State Tournament send off with Athletics dept.
Identify fundraising efforts of the Booster Club and maximize revenue | SLSF/ Superintendent of Recreation | Liz/Rachel | Q1: Create calendar of events Q2: Dine to Donate and Store Q3: Dine to Donate and Store Q4: Look at 2023 ideas | Q1: Calendar of events created. Q2: Dine to Donate and Apparel Store Q3: Dine to Donate and Apparel Store
Focus 1D. Identify collaborative opportunities with external organizations, corporations, groups and other entities
Goal | Department | Point Person | Quarter Objective | Objective Completed
Identify large companies and corporations that align with SLSF efforts. | SLSF | Anne | Q1: Create list of large corporations surrounding each programming site. Q2: Research company values and make list of those that align. Q3: Research grant opportunities from companies with aligned values, target 10 companies for payroll deductions/volunteering Q4: Assign projects to grant opportunities. | Q1: 22 Companies added to list Q2: LOIs sent to 7 companies Q3: LOI's sent to total of 8 companies. New grant submitted to North Shore Community Health Systems.
Identify agencies, organizations, groups, and businesses that support community initiatives within the NWSRA footprint | SLSF | Liz | Q1: Update list of organizations surrounding each programming site. Q2: Research company values and make list of those that align. Q3: Target aligned organization for sponsorship, donation, and volunteer opportunities Q4: Adjust marketing based on feedback and expand targeted list. | Q1: Updated tracker with 500 companies. Entered all local chamber listings. Q2: Lists expanded and continually updated. Utilized village websites. Q3: Targeted expanded lists used to target companies to support events in their community.
Focus 1E. Identify collaborative opportunities with external organizations, corporations, groups and other entities
Goal | Department | Point Person | Quarter Objective | Objective Completed
Expand relationships with organizations and groups within the NWSRA footprint who have a special interest in Diversity, Equity, and Inclusion. | SLSF | Anne/Liz | Q1: Identify 5 entities near each of the 6 programming sites. Q2: Strategize partnerships, which groups to reach out to. Q3: Set meetings with at least 3 groups. Q4: Incorporate ideas from meetings into events and marketing. | Q1: Palatine Coalition, Hanover Park Diversity, Palatine Library, Buffalo Grove PRIDE. Had meeting with Hispanic Chamber. Q2: Joined Diversity Section of AFP. Communicated with NWSRA staff to strategize which DEI community group to join. Communicating with Harper College office of DEI.
Goal Carried over from the 2021 Strategic Plan

## 2- Marketing-Communication
Strategy 2A. Create a Marketing Plan for each individual event
Goal | Department | Point Person | Quarter Objective | Objective Completed
Develop a marketing plan that identifies social media posts, electronic mail and other materials to be shared for each event | Marketing | Tom/Erika | Q1: Develop marketing plan template for all events. Q2: Fill marketing plan templates for each event - have marketing strategy meeting for each event. Q3: Execute and streamline marketing timelines. Q4: Review 2022 marketing strategy results, prep for 2023. | Q1. Completed marketing plan templates for all events. Q2: All event marketing plans are complete and event meetings are being held. Q3: Executing marketing timelines, designing re-engagement email campaign.
|  | Liz Thomas Emily Nock |  | Q1.
Strategy 2B. Utilize target marketing to reach specific groups
Goal | Department | Point Person | Quarter Objective | Objective Completed
Develop target market groups and develop materials. | SLSF/Marketing | Tom/Erika | Q1: Define and identify target market groups. Q2: Plan strategy for delivering targeted materials. Q3: Develop targeted materials for all groups. Q4: Implement targeted marketing. | Q1: Market Groups identified Q2: Use Marketing meetings to target specific groups. Create pieces for each market Q3: Executed targeted marketing for golf season.
Include stories on the impact that donations make (from past donors) | SLSF/Marketing | Tom/Erika | Ongoing - collect quotes, photos, and videos of impact Q1: Include event follow up with photos and amount raised after events. Q2: Outline follow up to donors about impact donation made. Q3: Start working on story for the holiday appeal and getting video, photos, and stories Q4: Send out Holiday Appeal with impact story, incorporate storytelling into the Celebrate Ability Gala through video and personal testimonies. | Q1: GMFS follow up posted to social media and emailed to attendees Q2: Commuicated amount raised for Bridges, Palatine, and virtual fundraisers. Included in event wrap ups. Q3: Decided on impact story for the holiday appeal and scheduled filming. Regular filming of impact taken at programs.
Strategy 2C. Continue to develop brand identification for each event
Goal | Department | Point Person | Quarter Objective | Objective Completed
Ensure that individual brand identification ties in with overall SLSF event | SLSF/Marketing | Tom/Erika | Q1: Establish individual brand for each event with marketing color scheme. Q2: Create website pages for each event with details. Q3: Execute new materials in marketing plan. Q4: Tie in event brands with sponsorship experience. | Q1: Redesigned event matgerials with matching color schemes across each event. Q2: Created individual event landing pages and overall event landing page. Q3: All event landing pages used for event promotion to drive traffic to SLSF website.
Develop closing materials showing impact. | SLSF/Marketing | Tom/Erika | Q1: Schedule film times to capture impact of donations at programming sites. Add impact stories to event timelines. Q2: Implement after events. Q3: Implement after events Q4: Implement after events and analyze results. | Q1: Filmed at Rolling Meadows sensory room, Broadway Buddies, Basketball Skills, and Spring Break Camps Q2: Filmed PURSUIT for closing materials. Q3: Event impact examples included in SLSF Impact newsletter.
Strategy 2D. Develop a diversity statement that addresses diversity, equity, and inclusion
Goal | Department | Point Person | Quarter Objective | Objective Completed
Develop a diversity, equity, and inclusion statement. | SLSF/Marketing | Anne/Tom/Erika | Q1: Research established DEI statements and create outline. Q2: Review outline, edit based on what is important to NWSRA/SLSF community. Q3: Final draft, present to the board for edits. Q4: Approved DEI statement plan for adding to marketing and implementation. | Q1: Outline for DEI statement structure complete based on DEI statement research. Q2: Reviewed draft and edited with NWSRA Marketing team. Q3: Extending drafting of DEI statement to include more input from community groups and NWSRA staff.
Goal Carried over from the 2021 Strategic Plan

## 3- Board Engagement
Strategy 3A. Direct specific asks to Board Members
Goal | Department | Point Person | Quarter Objective | Objective Completed
Identify the specific areas of need, communicate the need, and provide clear deadline for when funds are needed | SLSF | Anne | Q1: Send update email to board about how to contribute to Q1 events. Q2: Send monthly email to board about how to contribute to Q2 events. Q3: Send monthly email to board about how to contribute to Q3 events. Q4: Send monthly email to board about how to contribute to Q4 events. | Q1: Adjusted board email schedule to work with Impact Newsletter schedule. Board update email highlighting events and opportunities sent in February. Q2: Updated board newsletter formate and schedule. Q3: Implementing new board update schedule.
Follow up with each Board Member to ensure that their individual Board commitment is met throughout the year | SLSF | Anne | Q1: Send previous year contributions and ask what they would like to help with in 2022. Schedule one-on-one meetings. Q2: Reach out to meet with board members who did have one on ones in Q1. Q3: Reach out to board members individually to foster engagement and revisit goals. Q4: Follow up regarding annual commitment, give opportunity to brainstorm increasing fundraising | Q1. 2021 Contributions sent and collecting 2022 commitment letters. Holding meetings with individual board members. Q2: Still holding one on one board member meetings as needed. Q3: 3 board members connected with, continuing to foster board connections.
5. Investigate and establish programs that could be fully or partially sustained by part-time staff but overseen by a CTRS.
Strategy 3B. Ask Board to assist in marketing and outreach efforts
Goal | Department | Point Person | Quarter Objective | Objective Completed
Revamp Board Ambassador Program and Materials. | SLSF/ Marketing | Anne/Tom | Q1: Review current ambassador program and materials. Q2: Update Board Ambassador materials and website Q3: Update the board on director's site and material updates. Q4: Update materials for 2023 - be ready to implement. | Q1: Review current ambassador program and materials. Outlining print and digital options. Q2: Board ambassador materials streamlined and being updated. Website reports and calendar up to date. Q3: Reviewed which materials would be print vs digital. Building printing materials into 2023 budget to disperse 2023.
Provide more information to Board Members on upcoming endeavors. | SLSF | Anne/Tom | Q1: Send update email with event information. Q2: Highlight new upcoming events at board meeting. Q3: Contact board members about volunteer opportunities. Q4: Provide information on event wrap ups in board correspondence. | Q1. Board update email sent including all upcoming events, preparation, and how to get involved or promote. Q2: Upcoming events highlighted at May board meeting and in Board Update. Q3: Communicated volunteer opportunities through board updates and individual emails. Board members volunteered at all golf outings, and 2 additional events.
Strategy 3C: Diversity, Equity, and Inclusion in the Board
Goal | Department | Point Person | Quarter Objective | Objective Completed
Board member recruiting through a diversity, equity, and inclusion lense. | SLSF | Tracey/Anne | Q1: Research and development of DEI statement. Q2: Increased involvement in DEI oriented groups. Q3: Continued participation in DEI groups. Q4: Identify 3-5 individuals to target for involvement (internal and external). | Q1. Attending diversity committee meetings in professional and community organizations. Researching large foundation DEI statements. Q2: Researching area DEI groups for involvement. Q3: Have found 3 and attended 2 DEI groups, continuing to locate more groups.
Goal Carried over from the 2021 Strategic Plan

## 4- Fundraising Vehicles-Methods
Strategy 4A: Build Major Gifts Program: Devote more time to personal cultivation of potential major donors, creating a robust moves management system, and updating donor messaging to be more personal and donor-centric, rather than transactional and organization-centric.
Goal | Department | Point Person | Quarter Objective | Objective Completed
Develop relationships with existing donors to increase their donation levels. | SLSF | Anne/Liz | Q1: Create sponsorship experience Q2: Research major gifts programs Q3: Target donors to spend time with them Q4: Request feedback on the experience | Q1: Waiting on Marketing Q2: Worked with Association of Fundraising Professionals to audit other major gifts programs. Q3: Built relationships with donors through events and outside volunteering.
Research and investigate new donors through various search engines, databases, Board Member contacts and existing relationships. | SLSF | Anne | Q1: Use newspaper to collect new ideas Q2: Update tracker from new chamber books Q3: Follow local social media groups for ideas Q4: Review tracker for 2023 moving some to inactive and gathering more from google maps | Q1: Collected new names in board member meetings, newspaper, and chamber events. Researched national donors through larger search engines. Q2: Updated list from chamber books: Arlington Heights, Mount Prospect, Hoffman Estates, Palatine, and Rolling Meadows Q3: Researched new granting organizations through search platforms, submitted LOI's
Strategy 4B: Target donors through current direct mail (annual appeal) program: Bring program in line with industry standards, and experimenting with strategic prospect mailing to acquire new donors.
Goal | Department | Point Person | Quarter Objective | Objective Completed
Reach out to new potential donors through the Annual Appeal. | SLSF/Marketing | Anne/Tom | Q1: Analyze data from previous annual appeal approaches - identify best strategies already attempted. Q2: Spring Appeal - change mailing approach to increase response. Include online donation option. Q3: Analyze Spring Appeal response and past Holiday Appeal response. Adjust approach for Holiday Appeal. Q4: Holiday Appeal - change mailing approach to increase response. Include online donation option. | Q1. Reviewed previous appeals year to year analyses. Identified broad approach with personal impact stories most successful. Q2: Expanded Spring Appeal contact list. Redesigned spring appeal and created online landing page. Q3: Expanding Holiday Appeal email list to reach more NWSRA families with no added cost.
Strategy 4C: 4. Create a planned giving program: Alert parents, grandparents, volunteers, and donors to the possibility of including SLSF in their legacy plans, while recognizing those that have already done so.
Goal | Department | Point Person | Quarter Objective | Objective Completed
Identify ways to enhance Planned Giving program | SLSF | Anne/Liz | Q1: Design Planned Giving portion of "In Memory Of" website. Q2: Written outline for Planned Giving Program. Q3: Research 2 successful examples from others Q4: Create roll out plan for 2023 | Q1: Waiting on marketing Q2. Touched base with marketing on estimated completion date Q3: Networking with fundraising professionals with planned giving experience. Meeting estate planning professionals.
Create "In Memory Of" donations program | SLSF/Marketing | Liz/Tom | Q1: Written outline Q2: Meeting about the plan Q3: Website completed and proofed Q4: Website announced and marketed | Q1: Outline completed Q2: Waiting on update from Marketing Q3: Waiting on update from Marketing.
Goal Carried over from the 2018-2020 Strategic Plan